## Cover
TEST REPORT DOCUMENT
Project Name | Artwork Sharing Platform Project |  |  | Creator | Group 1
Project Code | ASP |  |  | Issue Date | 2024-03-21
Document Code | ASP |  |  | Version
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
Note on D10: ====== ID#AAAA4IanTyo (2023-09-09 06:57:24) *A: Add M: Modify D: Delete

## Test Cases
TEST CASE LIST
Project Name |  | Artwork Sharing Platform Project
Project Code |  | ASP
Test Environment Setup Description |  | 1. API 2. Web Browser
No | Function Name | Sheet Name | Description | Pre-Condition
1 | New Customer | New Customer | Add new customer | New Customer (API)'
2 | Edit Customer | Edit Customer | Edit Customer | New Customer
3 | New Account | New Account | Add new account
4 | Edit Account | Edit Account | Edit Account | New Account

## Test Statistics
TEST STATISTICS
Project Name | Banking Project |  | Creator |  |  | Chi Le
Project Code | BP |  | Reviewer/Approver
Document Code | BP_Test Report |  | Issue Date |  |  | 2024-01-11
Notes
No | Module code | Passed | Failed | Pending | N/A | Number of test cases
1 | New Account | 13 | 8 | 0 | 0 | 21
2 | Edit New Account | 17 | 4 | 0 | 0 | 21
3 | New Customer | 49 | 44 | 0 | 0 | 93
4 | Edit New Customer | 50 | 22 | 0 | 0 | 72
| Sub total | 129 | 78 | 0 | 0 | 207
| Test coverage |  | 100 | %
| Test successful coverage |  | 62.3188 | %

## (API)
Feature | API | [13 empty] | Passed
Test requirement | API of Authentication and Authorization | [13 empty] | Failed
Number of TCs | 94 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 94 | 0 | 0 | 0
Round 2 | 94 | 0 | 0 | 0
Round 3 | 94 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Login | Login
AT01 | Login sucessfully as a Admin Account | 1. Send a request login by JSON 2. Click button send on Postman | Status code is 200 - return new token string of that account | email: "thuc@example.com" password:"1" | Passed | 2023-09-25 | Tom | Passed | 2023-09-25 | Jenni | Passed | 2023-09-25 | Luke
AT02 | Login fail as Admin Account | 1. Send a request login by JSON 2. Click button send on Postman | Status code is 406 - return with error message | email: "thuc@example.com" password:"2" | Passed | 2023-09-25 | Tom | Passed | 2023-09-25 | Jenni | Passed | 2023-09-25 | Luke
AT03 | Login successfully as Customer | 1. Send a request login by JSON 2. Click button send on Postman | Status code is 200 - return new token string of that account | email: "alice.j@example.com" password:"1" | Passed | 2023-09-25 | Tom | Passed | 2023-09-25 | Jenni | Passed | 2023-09-25 | Luke
AT04 | Login fail as Customer | 1. Send a request login by JSON 2. Click button send on Postman | Status code is 406 - return with error message | email: "alice.j@example.com" password:"2" | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT05 | Login successfully as Creator | 1. Send a request login by JSON 2. Click button send on Postman | Status code is 200 - return new token string of that account | email: "bob.smith@example.com" password:"1" | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT06 | Login fail as Creator | 1. Send a request login by JSON 2. Click button send on Postman | Status code is 406 - return with error message | email: "bob.smith@example.com" password:"2" | Passed | 2023-09-27 | Tom | Passed | 2023-09-27 | Jenni | Passed | 2023-09-27 | Luke
Logout
AT07 | Logout from Customer | 1. Send a request logout by Header token 2. Click button send on Postman | Status code is 204 - logout from the customer's account | Have logged into a customer's account | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT08 | Logout from Creator | 1. Send a request logout by Header token 2. Click button send on Postman | Status code is 204 - logout from the creator's account | Have logged into a creator's account | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT09 | Logout from Admin | 1. Send a request logout by Header token 2. Click button send on Postman | Status code is 204 - logout from the admin's account | Have logged into a admin's account | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Get logged account info
AT10 | Get account info successfully | 1. Send a request get info by Header token 2. Click button send on Postman | Status code is 202 - return with user info | Token that is login token, valid and not expired | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT11 | Get account info fail | 1. Send a request get info by Header token 2. Click button send on Postman | Status code is 401 - return with error message | Token that is not login token, invalid or expired | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Register
AT12 | Register successfully | 1. Send a request register by JSON 2. Click button send on Postman | Status code is 201 - return with token login string | Email have not yet registered | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT13 | Register fail | 1. Send a request register by JSON 2. Click button send on Postman | Status code is 409 - return with error message | Email have registered | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Change password
AT14 | Change password successfully | 1. Send a request change password by JSON and Header 2. Click button send on Postman | Status code is 200 | Correct old password | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT15 | Change password fail | 1. Send a request change password by JSON and Header 2. Click button send on Postman | Status code is 401 - return with error message | Incorrect old password | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Change password
AT16 | Get reset password token successfully | 1. Send a request get reset password token by JSON 2. Click button send on Postman | Status code is 202 - return with token string | Email exists | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT17 | Get reset password token fail | 1. Send a request get reset password token by JSON 2. Click button send on Postman | Status code is 404 - return with error message | Email does not exist | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT18 | Reset password successfully | 1. Send a request get reset password token by JSON 2. Click button send on Postman | Status code is 204 | Correct token | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT19 | Reset password fail | 1. Send a request get reset password token by JSON 2. Click button send on Postman | Status code is 401 - return with error message | Incorrect token | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Get all artwork
AT20 | Get all artwork successfully | 1. Click button send on Postman | Status code is 200 - return with list artwork |  | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Get specific artwork
AT21 | Get specific artwork successfully | 1. Send a request get artwork by path 2. Click button send on Postman | Status code is 200 - return with artwork | Enter the artwork Id that exists | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT22 | Get specific artwork fail | 1. Send a request get artwork by path 2. Click button send on Postman | Status code is 404 - return with error message | Enter Artwork Id does not exist | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Get artwork by title
AT23 | Get list artwork successfully | 1. Send a request get artwork by path 2. Click button send on Postman | Status code is 200 - return with artwork | Enter part of title | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT24 | Get list artwork fail | 1. Send a request get artwork by path 2. Click button send on Postman | Status code is 404 - return with error message | Do not enter path param or enter a not exist title | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Get artwork by type
AT25 | Get list artwork successfully | 1. Send a request get artwork by path 2. Click button send on Postman | Status code is 200 - return with artwork | Enter part of type | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT26 | Get list artwork fail | 1. Send a request get artwork by path 2. Click button send on Postman | Status code is 404 - return with error message | Do not enter path param or enter a not exist type | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Get artwork by creator
AT27 | Get list artwork successfully | 1. Send a request get artwork by path 2. Click button send on Postman | Status code is 200 - return with artwork | Enter part of creator | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT28 | Get list artwork fail | 1. Send a request get artwork by path 2. Click button send on Postman | Status code is 404 - return with error message | Do not enter path param or enter a not exist creator | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Comment an artwork
AT29 | Comment an artwork | 1. Send a request comment by JSON and Header 2. Click button send on Postman | Status code is 200 - return with comment | Artwork exist | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT30 | Get all comment of an artwork successfully | 1. Send a request get comment by path 2. Click button send on Postman | Status code is 200 - return with comment | Artwork exist and have comment | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT31 | Get all comment of an artwork fail | 1. Send a request get comment by path 2. Click button send on Postman | Status code is 404 - return with error message | Artwork exist and have no comment | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Reaction an artwork
AT32 | Reaction an artwork | 1. Send a request reactioin by JSON and Header 2. Click button send on Postman | Status code is 204 | Artwork exist | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT33 | Get all reaction of an artwork successfully | 1. Send a request get reaction by path 2. Click button send on Postman | Status code is 200 - return with user | Artwork exist and have reaction | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT34 | Get all reaction of an artwork fail | 1. Send a request get reaction by path 2. Click button send on Postman | Status code is 404 - return with error message | Artwork exist and have no reaction | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Favorite an artwork
AT35 | Favorite an artwork | 1. Send a request reaction by JSON and Header 2. Click button send on Postman | Status code is 204 | Artwork exist | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT36 | Get all favorite of an user successfully | 1. Send a request get reaction by path 2. Click button send on Postman | Status code is 200 - return with artwork | User has favorite | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT37 | Get all favorite of an user fail | 1. Send a request get reaction by path 2. Click button send on Postman | Status code is 404 - return with error message | User does not have favorite | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Sell artwork
AT38 | Sell an artwork succesfully | 1. Send a request sell artwork by JSON and Header 2. Click button send on Postman | Status code is 200 - return with artwork | User own the artwork | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT39 | Sell an artwork fail | 1. Send a request sell artwork by JSON and Header 2. Click button send on Postman | Status code is 401 - return with error message | User does not own the artwork | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Update artwork
AT40 | Update an artwork successfully | 1. Send a request update artwork by JSON and Header 2. Click button send on Postman | Status code is 200 - return with artwork | Valid token and owner of the artwork | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT41 | Update an artwork fail | 1. Send a request update artwork by JSON and Header 2. Click button send on Postman | Status code is 403 - return error message | Not owner of the artwork | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Delete artwork
AT42 | Delete an artwork successfully | 1. Send a request delete artwork by JSON and Header 2. Click button send on Postman | Status code is 200 - return with artwork | Valid token and owner of the artwork | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT43 | Delete an artwork fail | 1. Send a request delete artwork by JSON and Header 2. Click button send on Postman | Status code is 403 - return error message | Not owner of the artwork | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Get top 10 artwork
AT44 | Get top 10 artwork successfully | 1. Send a request get artwork 2. Click button send on Postman | Status code is 200 - return with artwork |  | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Report artwork
AT45 | Report an artwork successfully | 1. Send a request report artwork by Json and Header 2. Click button send on Postman | Status code is 204 | Artwork exists | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT46 | Report an artwork fail | 1. Send a request report artwork by Json and Header 2. Click button send on Postman | Status code is 404 - return with error message | Artwork does not exist | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Get all report
AT47 | Get all report successfully | 1. Send a request get report by Header 2. Click button send on Postman | Status code is 200 - return with report | use admin's account | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT48 | Get all report fail | 1. Send a request get report by Header 2. Click button send on Postman | Status code is 403 - return error message | not admin account | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT49 | Get all report fail | 1. Send a request get report by Header 2. Click button send on Postman | Status code is 404 - return error message | Does not have any report | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Process report
AT50 | Get all report successfully | 1. Send a request process report by Path param Header, JSON 2. Click button send on Postman | Status code is 404 - return error message | use admin's account | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT51 | Get all report fail | 1. Send a request process report by Path param Header, JSON 2. Click button send on Postman | Status code is 403 - return error message | not admin account | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT52 | Get all report fail | 1. Send a request process report by Path param Header, JSON 2. Click button send on Postman | Status code is 404 - return error message | Report has been processed | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Get cart
AT53 | Get all artwork in cart successfully | 1. Send a request get artwork from cart by Header 2. Click button send on Postman | Status code is 200 - return with artwork | valid token | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Add to cart
AT54 | Add artwork to cart successfully | 1. Send a request add artwork to cart by Header, JSON 2. Click button send on Postman | Status code is 200 - return with cart | Artwork does not remove, ban, or private | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT55 | Add artwork to cart fail | 1. Send a request add artwork to cart by Header, JSON 2. Click button send on Postman | Status code is 403 - return error message | Artwork remove, ban, or private | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Delete to cart
AT56 | Delete artwork from cart successfully | 1. Send a request from artwork to cart by Header, JSON 2. Click button send on Postman | Status code is 200 - return with cart | Artwork exists in cart | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Get all user
AT57 | Get all user successfully | 1. Send a request get user 2. Click button send on Postman | Status code is 200 - return with user |  | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Get 10 user
AT58 | Get 10 user successfully | 1. Send a request get user 2. Click button send on Postman | Status code is 200 - return with user |  | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Create order
AT59 | Create order successfully | 1. Send a request create order by JSON, Header 2. Click button send on Postman | Status code is 200 - return with order and artwork | Cart does not empty | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT60 | Create order fail | 1. Send a request create order by JSON, Header 2. Click button send on Postman | Status code is 406 - return with error message | Cart empty | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Get order history
AT61 | Get all order that user has been ordered | 1. Send a request get order by Header 2. Click button send on Postman | Status code is 200 - return with order and artwork |  | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT62 | Get all order that user has been received | 1. Send a request get order by Header 2. Click button send on Postman | Status code is 200 - return with order and artwork |  | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Get order
AT63 | Get all order | 1. Send a request get order by Header 2. Click button send on Postman | Status code is 200 - return with order and artwork |  | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT64 | Get top 10 order | 1. Send a request get order by Header 2. Click button send on Postman | Status code is 200 - return with order and artwork |  | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Get favorite artwork
AT65 | Get all artwork that user favorite | 1. Send a request get artwork by Header 2. Click button send on Postman | Status code is 200 - return with order and artwork |  | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Follow user
AT66 | Follow a user | 1. Send a request follow user by Header, path param 2. Click button send on Postman | Status code is 200 | Not yet followed | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT67 | Unfollow a user | 1. Send a request unfollow user by Header, path param 2. Click button send on Postman | Status code is 200 | Has followed | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT68 | Get following user | 1. Send a request get following user by path param 2. Click button send on Postman | Status code is 200 |  | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT69 | Get follower user | 1. Send a request get follower user by path param 2. Click button send on Postman | Status code is 200 |  | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Publish artwork
AT70 | Publish an artwork succesfully | 1. Send a request publish artwork by JSON and Header 2. Click button send on Postman | Status code is 200 - return with artwork |  | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Get user profile
AT71 | Get user profile | 1. Send a request user profile by Header 2. Click button send on Postman | Status code is 200 - return with user |  | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Update user
AT72 | Update user | 1. Send a request update user by Header, JSON 2. Click button send on Postman | Status code is 200 |  | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT73 | Ban user | 1. Send a request ban user by Header, path param 2. Click button send on Postman | Status code is 200 | Admin's account | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
AT74 | Unban user | 1. Send a request unban user by Header, path param 2. Click button send on Postman | Status code is 200 | Admin's account | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Jenni | Passed | 2023-09-26 | Luke
Request
AT75 | View all request from one member that have request | 1. Send a request view by authtoken 2. Click send on Postman | Status code is 200 - ok | Have logged into a member's account | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat
AT76 | View all request from one member that do not have request | 1. Send a request view by authtoken 2. Click send on Postman | Status code is 204 - No content | Have logged into a member's account | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat
AT77 | View request by id | 1. Send a request view by authtoken 2. Click send on Postman | Status code is 200 - ok | Have logged into a member's account | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat
AT78 | Create request | 1. Send a request view by authtoken 2. Send a request by JSON 3. Click send on Postman | Status code is 200 - ok | Have logged into a member's account | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat
AT79 | Update request that correct owner request | 1. Send a request view by authtoken 2. Send a request by JSON 3. Click send on Postman | Status code is 200 - ok | Have logged into a member's account | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat
AT80 | Update request that incorrect owner request | 1. Send a request view by authtoken 2. Send a request by JSON 3. Click send on Postman | Status code is 401 - Unauthorized | Have logged into a member's account | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat
AT81 | Delete request that incorrect owner request | 1. Send a request view by authtoken 2. Send a request report Id by pathParam 3. Click send on Postman | Status code is 401 - Unauthorized | Have logged into a member's account | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat
AT82 | Delete request that correct owner request | 1. Send a request view by authtoken 2. Send a request report Id by pathParam 3. Click send on Postman | Status code is 200 - ok | Have logged into a member's account | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat
AT83 | Delete request that correct publisher request | 1. Send a request view by authtoken 2. Send a request report Id by pathParam 3. Click send on Postman | Status code is 200 - ok | Have logged into a member's account | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat
AT84 | Approve/Reject request that incorrect publisher request | 1. Send a request view by authtoken 2. Send a request report Id by pathParam 3. Click send on Postman | Status code is 401 - Unauthorized | Have logged into a member's account | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat
AT85 | Seen request that incorrect publisher request | 1. Send a request view by authtoken 2. Send a request report Id by pathParam 3. Click send on Postman | Status code is 401 - Unauthorized | Have logged into a member's account | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat
AT86 | Seen request that correct publisher request | 1. Send a request view by authtoken 2. Send a request report Id by pathParam 3. Click send on Postman | Status code is 200 - ok | Have logged into a member's account | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat
AT87 | Response request that correct publisher request | 1. Send a request view by authtoken 2. Send a request report Id by pathParam 3. Click send on Postman | Status code is 200 - ok | Have logged into a member's account | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat
AT88 | Response request that incorrect publisher request | 1. Send a request view by authtoken 2. Send a request report Id by pathParam 3. Click send on Postman | Status code is 401 - Unauthorized | Have logged into a member's account | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat
AT89 | Remove request that incorrect publisher request | 1. Send a request view by authtoken 2. Send a request report Id by pathParam 3. Click send on Postman | Status code is 401 - Unauthorized | Have logged into a member's account | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat
AT90 | Remove request that correct publisher request | 1. Send a request view by authtoken 2. Send a request report Id by pathParam 3. Click send on Postman | Status code is 200 - ok | Have logged into a member's account | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat | Passed | 2024-03-16 | Dat
Response
AT91 | Response a request | 1. Send a request login by Headers: authtoken 2. Send a request login by JSON 3. Click button execute on Swagger" | Status code is 200 | Have logged into creater account and own this request Insert responseId by PathParam | Passed | 2024-03-16 | Do The Hieu | Passed | 2024-03-16 | Do The Hieu | Passed | 2024-03-16 | Do The Hieu
AT92 | Get all response | 1. Send a request login by Headers: authtoken 2. Click button execute on Swagger | Status code is 200 | Have logged into creater account and own this request Insert responseId by PathParam | Passed | 2024-03-16 | Do The Hieu | Passed | 2024-03-16 | Do The Hieu | Passed | 2024-03-16 | Do The Hieu
AT93 | Get response by id | 1. Send a request login by Headers: authtoken 2. Click button execute on Swagger | Status code is 200 | Have logged into creater account and own this request Insert responseId by PathParam | Passed | 2024-03-16 | Do The Hieu | Passed | 2024-03-16 | Do The Hieu | Passed | 2024-03-16 | Do The Hieu
AT94 | Delete response | 1. Send a request login by Headers: authtoken 2. Click button execute on Swagger | Status code is 200 | Have logged into creater account and own this request Insert responseId by PathParam | Passed | 2024-03-16 | Do The Hieu | Passed | 2024-03-16 | Do The Hieu | Passed | 2024-03-16 | Do The Hieu
Note on E10: ====== ID#AAAA4IanTyk tqsang (2023-09-09 06:57:24) List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Edit Customer
Feature | Edit Customer | [13 empty] | Passed
Test requirement | Mobile application and Web browser of Edit Customer | [13 empty] | Failed
Number of TCs | 21 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 5 | 2 | 0 | 0
Round 2 | 6 | 1 | 0 | 0
Round 3 | 6 | 1 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Login | Login
EC01 | Login sucessfully as a Admin Account | 1. Admin enter correct username and password in Login page 2. Press login button | Application redirect to admin home page and pop up message "Login successfully" | username: "foxmanager" password:"zaQ@1234" | Passed | 2023-09-25 | Tom | Passed | 2023-09-25 | Luke | Passed | 2023-09-25 | Handy
ED02 | Login fail as Admin Account | 1. Admin enter incorrect username and password in Login page 2. Press login button | Application pop up message "Wrong username or password" | username: "foxmanager" password:"zaQ@" | Passed | 2023-09-25 | Tom | Passed | 2023-09-25 | Luke | Passed | 2023-09-25 | Handy
ED03 | Login successfully as Customer by OTP | 1. Customer choose "Đăng nhập bằng mã OTP" button in Login page 2. Enter user phone number 3. Wait for OTP code to be sent via sms message 4. Enter OTP code and press confirm button | Application redirect to customer home page and pop up message "Login successfully" | isPhone: true, idToken: "", fcmToken: "" | Failed | 2023-09-25 | Tom | Passed | 2023-09-25 | Luke | Passed | 2023-09-25 | Handy | Round 1: Application do not redirect to home page
ED04 | Login successfully as Customer by email | 1. Customer choose "Đăng nhập bằng email" button in Login page 2. User enter email and password 3. Confirm email and password | Application redirect to customer home page and pop up message "Login successfully" | isPhone: true, idToken: "", fcmToken: "" | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Luke | Passed | 2023-09-26 | Handy
ED05 | Login successfully as Staff | 1. Staff enter username and password in Login page 2. Press login button | Application redirect to staff home page and pop up message "Login successfully" | username: "staff" password:"zaQ@1234" | Failed | 2023-09-26 | Tom | Failed | 2023-09-26 | Luke | Failed | 2023-09-26 | Handy | Round 1: Pop up "incorrect username or password"
ED06 | Login successfully as Shipper | 1. Shipper enter username and password in Login page 2. Press login button | Application redirect to shipper home page and pop up message "Login successfully" | username: "shipper" password:"zaQ@1234" | Passed | 2023-09-27 | Tom | Passed | 2023-09-27 | Luke | Passed | 2023-09-27 | Handy
Logout
ED07 | Logout from Customer | 1. Customer click to "Logout" button | Application redirect to login page | Have logged into a customer's account | Passed | 2023-09-26 | Tom | Passed | 2023-09-26 | Luke | Passed | 2023-09-26 | Handy